CLINIC MANAGEMENT SYSTEM

Sprint Planning & Project Timeline

Version 2.0  |  April 2026  |  4 Developers  |  2-Week Sprints  |  12 Weeks Total

| 6 Sprints | 3 Weeks | 176 Story Points | 45 User Stories | 10 Epics |
| --- | --- | --- | --- | --- |

| 👥 Team 4 Developers | ⏱ Sprint 2 Weeks Each | 🚀 Start Week 1 | 🏁 End Week 12 |
| --- | --- | --- | --- |

PART 1 — PLANNING ASSUMPTIONS & TEAM SETUP

| Parameter | Value |
| --- | --- |
| Team Composition | 6 developers: 4 Backend, 2 Frontend |
| Sprint Duration | week per 2 sprint |
| Sprint Velocity | 17 – 37 story points / sprint (avg ~29 pts) |
| Working Hours | 8 hrs/day per developer • 20% buffer for reviews, bugs & meetings |
| Ceremonies | Daily standup 15 min • Sprint review + retro end of each sprint |
| Definition of Ready | Story has: acceptance criteria ✓ dependencies resolved ✓ estimate agreed ✓ |
| Definition of Done | Code reviewed ✓ unit tested ✓ integrated ✓ AC passed ✓ deployed to staging ✓ |
| Tech Stack | Node.js API + React Frontend + PostgreSQL + Redis (queue) + Object Storage (files) |
| Risk Buffer | 20% of each sprint capacity reserved for bugs, tech debt & integration issues |
| Priorities | High → must ship in assigned sprint ¦ Medium → can slip 1 sprint ¦ Low → nice-to-have |

PART 2 — PROJECT TIMELINE (12-WEEK GANTT)

كل صف = sprint واحد مدته أسبوعين. الخلايا الملوّنة هي أسابيع الـ sprint النشط.

| Sprint | W1 | W1 | W1 | W1 | W2 | W2 | W2 | W2 | W3 | W3 | W3 | W3 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S1: Security & System 37pts | ▓ | ▓ |  |  |  |  |  |  |  |  |  |  |
| S2: Doctors, Staff & 17pts |  |  | ▓ | ▓ |  |  |  |  |  |  |  |  |
| S3: Patient Management & 37pts |  |  |  |  | ▓ | ▓ |  |  |  |  |  |  |
| S4: Check-In, Queue & 36pts |  |  |  |  |  |  | ▓ | ▓ |  |  |  |  |
| S5: Medical Records, Billing 31pts |  |  |  |  |  |  |  |  | ▓ | ▓ |  |  |
| S6: Reports, Dashboard & 18pts |  |  |  |  |  |  |  |  |  |  | ▓ | ▓ |
| Wave | Wave 1 | Wave 1 | Wave 1 | Wave 1 | Wave 2 | Wave 2 | Wave 3 | Wave 3 | Wave 4 | Wave 4 | Wave 5 | Wave 5 |

ملخص الـ Sprints والـ Velocity:

| Sprint | Title | Stories | Points | Weeks | Velocity* | % Done |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | Security & System Foundation | 7 | 37 | 2 | 4.6 pt/dev/wk | 21% |
| Sprint 2 | Doctors, Staff & Rooms Setup | 5 | 17 | 2 | 2.1 pt/dev/wk | 31% |
| Sprint 3 | Patient Management & Appointment Booking | 8 | 37 | 2 | 4.6 pt/dev/wk | 52% |
| Sprint 4 | Check-In, Queue & Consultation | 11 | 36 | 2 | 4.5 pt/dev/wk | 72% |
| Sprint 5 | Medical Records, Billing & Notifications | 10 | 31 | 2 | 3.9 pt/dev/wk | 90% |
| Sprint 6 | Reports, Dashboard & Final QA | 4 | 18 | 2 | 2.3 pt/dev/wk | 100% |
| TOTAL — 45 Stories |  | 45 | 176 | 12 | — | 100% |

* Velocity = story points ÷ (4 developers × weeks). Target ≈ 3-4 pts per developer per week.

PART 3 — SPRINT-BY-SPRINT DETAIL

| Sprint 1 — Security & System Foundation Wave 1 — Foundation ¦ Weeks 1–2 ¦ Start: April 2026 | 7 Stories | 37 Points | 2wk Duration |
| --- | --- | --- | --- |

| SPRINT GOAL | تأسيس Authentication وRBAC وكل الكيانات الأساسية حتى كل feature تانية تبني على قاعدة آمنة ومُعدَّة. |
| --- | --- |

| ID | User Story | Actor | Pts | Priority | Depends On |
| --- | --- | --- | --- | --- | --- |
| US-042 | User Authentication (Login & Logout) | All Users | 5 | High | — |
| US-043 | Role-Based Access Control (RBAC) | System | 8 | High | US-042 |
| US-044 | Audit Trail — Log All System Actions | System | 5 | High | US-042 |
| US-045 | Security Rules (Session Timeout / Password) | System | 5 | High | US-042 |
| US-001 | Create & Manage Departments | Admin | 3 | High | US-043 |
| US-006 | Define Roles & Permissions | Admin | 8 | High | US-043 |
| US-007 | Configure System Settings | Admin | 3 | Medium | US-043 |
| SPRINT TOTAL |  |  | 37 |  |  |

| ✓ Definition of Done | ⚠ Risks |
| --- | --- |
| ✓; كل endpoints مأمّنة بـ HTTPS + JWT صالح. | ⚠; RBAC scope قد يتوسع أثناء التنفيذ. |
| ✓; Permission matrix مُحمَّل في الـ database. | ⚠; Audit log performance تحت الضغط. |
| ✓; Audit log يسجّل كل write action. | — |
| ✓; Departments وSystem Settings قابلة للإدارة. | — |
| ✓; Role change يُنهي الـ session فوراً. | — |

| Sprint 2 — Doctors, Staff & Rooms Setup Wave 1 — Foundation ¦ Weeks 3–4 ¦ Start: April 2026 | 5 Stories | 17 Points | 1/2wk Duration |
| --- | --- | --- | --- |

| SPRINT GOAL | استكمال directory العيادة — doctors، staff accounts، work schedules، وrooms — حتى الـ booking engine عنده كل البيانات المطلوبة. |
| --- | --- |

| ID | User Story | Actor | Pts | Priority | Depends On |
| --- | --- | --- | --- | --- | --- |
| US-002 | Add & Manage Doctors | Admin | 5 | High | US-001 |
| US-003 | Set Doctor Work Schedules | Admin | 5 | High | US-002, US-007 |
| US-004 | Create & Manage Rooms (Fixed Room Logic) | Admin | 2 | High | US-001 |
| US-005 | Add Staff Members (Receptionist & Nurse) | Admin | 3 | High | US-006 |
| US-033 | Manage Services & Pricing | Admin | 2 | Medium | US-007 |
| SPRINT TOTAL |  |  | 17 |  |  |

| ✓ Definition of Done | ⚠ Risks |
| --- | --- |
| ✓; Doctor profiles نشطة ومرتبطة بـ departments. | ⚠; Slot generation logic معقّدة. |
| ✓; Weekly schedules بتولّد slots صح. | ⚠; Room-department validation edge cases. |
| ✓; Staff accounts بتشتغل بـ role-based login. | — |
| ✓; Rooms مع department + doctor mapping. | — |
| ✓; Services catalogue جاهز للـ billing. | — |

| Sprint 3 — Patient Management & Appointment Booking Wave 2 — Core Operations ¦ Weeks 5–6 ¦ Start: April 2026 | 8 Stories | 37 Points | 1/2wk Duration |
| --- | --- | --- | --- |

| SPRINT GOAL | تفعيل رحلة المريض الكاملة في الـ front-desk: تسجيل، بحث، ملف، عرض slots، وحجز مواعيد بـ atomic conflict prevention. |
| --- | --- |

| ID | User Story | Actor | Pts | Priority | Depends On |
| --- | --- | --- | --- | --- | --- |
| US-008 | Search for Existing Patient | Receptionist | 3 | High | US-009 |
| US-009 | Register New Patient | Receptionist | 3 | High | — |
| US-010 | View & Update Patient Profile | Recept./Doctor | 3 | Medium | US-009 |
| US-011 | View Available Appointment Slots | Receptionist | 5 | High | US-002,003,007 |
| US-012 | Book an Appointment | Receptionist | 8 | High | US-009,011 |
| US-013 | Validate Slot Availability (System) | System | 5 | High | US-012 |
| US-014 | Auto-Assign Room (Fixed→Dept→Manual) | System | 5 | High | US-004,012 |
| US-015 | Cancel or Reschedule Appointment | Receptionist | 5 | High | US-012 |
| SPRINT TOTAL |  |  | 37 |  |  |

| ✓ Definition of Done | ⚠ Risks |
| --- | --- |
| ✓; Patient registration مع duplicate-phone detection. | ⚠; Concurrent booking race conditions. |
| ✓; Real-time slot availability calendar. | ⚠; Room assignment fallback edge cases. |
| ✓; Booking بيعمل Scheduled appointment atomically. | — |
| ✓; Room auto-assigned بـ 3-step algorithm. | — |
| ✓; Cancel/Reschedule بيحرر الـ slot والـ room. | — |

| Sprint 4 — Check-In, Queue & Consultation Wave 3 — Clinical Flow ¦ Weeks 7–8 ¦ Start: April 2026 | 11 Stories | 36 Points | 1/2wk Duration |
| --- | --- | --- | --- |

| SPRINT GOAL | تسليم الـ clinical workflow الكامل: check-in → queue management → consultation → diagnosis + prescription + record completion. |
| --- | --- |

| ID | User Story | Actor | Pts | Priority | Depends On |
| --- | --- | --- | --- | --- | --- |
| US-016 | Check-In Patient on Arrival | Receptionist | 3 | High | US-012 |
| US-017 | Add Patient to Queue (System) | System | 3 | High | US-016 |
| US-018 | Prioritize Patient in Queue | Recept./Doctor | 3 | Medium | US-017 |
| US-019 | Skip or Recall Patient in Queue | Doctor | 3 | Medium | US-017 |
| US-020 | Call Next Patient | Doctor | 3 | High | US-017 |
| US-021 | Open Appointment & View Medical History | Doctor | 5 | High | US-020 |
| US-022 | Write & Save Diagnosis | Doctor | 3 | High | US-021 |
| US-023 | Write Prescription | Doctor | 3 | High | US-021 |
| US-024 | Add Consultation Notes | Doctor | 2 | Medium | US-021 |
| US-025 | Define Follow-Up Appointment | Doctor | 3 | Medium | US-021 |
| US-026 | Auto-Save Medical Record on Completion | System | 5 | High | US-022 |
| SPRINT TOTAL |  |  | 36 |  |  |

| ✓ Definition of Done | ⚠ Risks |
| --- | --- |
| ✓; Check-in بيغيّر الـ status ويضيف للـ queue. | ⚠; Real-time queue sync (WebSocket vs polling). |
| ✓; FIFO queue مع priority/skip/recall شغّال. | ⚠; Atomic record save عند إنهاء الـ consultation. |
| ✓; Call-next بيفتح consultation view. | — |
| ✓; Diagnosis + prescription محفوظين في المِلف. | — |
| ✓; Appointment status = Completed atomically. | — |

| Sprint 5 — Medical Records, Billing & Notifications Wave 4 — Billing & Enhancement ¦ Weeks 9–10 ¦ Start: April 2026 | 10 Stories | 31 Points | 1/2wk Duration |
| --- | --- | --- | --- |

| SPRINT GOAL | استكمال دورة ما بعد الـ consultation: رفع ملفات طبية، billing كامل (invoice → payment → receipt)، وكل الإشعارات التلقائية. |
| --- | --- |

| ID | User Story | Actor | Pts | Priority | Depends On |
| --- | --- | --- | --- | --- | --- |
| US-027 | Upload Medical Attachments | Doctor | 5 | Medium | US-026 |
| US-028 | View Complete Medical History | Doctor/Staff | 3 | High | US-026 |
| US-029 | Create Invoice | Receptionist | 5 | High | US-026,033 |
| US-030 | Calculate Invoice Total (System) | System | 2 | High | US-029 |
| US-031 | Process Payment | Receptionist | 3 | High | US-029 |
| US-032 | Generate Receipt (System) | System | 3 | High | US-031 |
| US-034 | Send Booking Confirmation Notification | System | 3 | High | US-012 |
| US-035 | Send Appointment Reminder Notification | System | 3 | Medium | US-034 |
| US-036 | Send Cancellation Notification | System | 2 | High | US-015 |
| US-037 | Send Payment Confirmation Notification | System | 2 | Medium | US-031,032 |
| SPRINT TOTAL |  |  | 31 |  |  |

| ✓ Definition of Done | ⚠ Risks |
| --- | --- |
| ✓; Files مرفوعة مع virus scan. | ⚠; PDF generation للـ receipts. |
| ✓; Invoice منشأ ومحسوب ومُصدَر. | ⚠; Notification retry queue reliability. |
| ✓; Payment مسجّل (full / partial). | — |
| ✓; Receipt مولَّد وقابل للإرسال بالإيميل. | — |
| ✓; كل الـ 4 notification triggers شغّالة. | — |

| Sprint 6 — Reports, Dashboard & Final QA Wave 5 — Analytics ¦ Weeks 11–12 ¦ Start: April 2026 | 4 Stories | 18 Points | 1/2wk Duration |
| --- | --- | --- | --- |

| SPRINT GOAL | تسليم Admin analytics dashboards وإنهاء regression testing وperformance validation وsign-off على الـ production readiness. |
| --- | --- |

| ID | User Story | Actor | Pts | Priority | Depends On |
| --- | --- | --- | --- | --- | --- |
| US-038 | View Patient Count Reports | Admin | 5 | High | All ops |
| US-039 | View Revenue Reports | Admin | 5 | High | Epic-07 |
| US-040 | View Doctor Performance Reports | Admin | 5 | Medium | Epic-05,07 |
| US-041 | View Room Utilization Reports | Admin | 3 | Low | US-004 |
| SPRINT TOTAL |  |  | 18 |  |  |

| ✓ Definition of Done | ⚠ Risks |
| --- | --- |
| ✓; الـ 4 reports بتتولّد بيانات صحيحة. | ⚠; Large dataset performance في الـ reports. |
| ✓; Date range + export شغّالين. | ⚠; Report PDF export generation. |
| ✓; End-to-end regression passed. | — |
| ✓; Performance benchmarks OK. | — |
| ✓; Security pen-test signed off. | — |

PART 4 — FULL PRODUCT BACKLOG (45 Stories)

| Sprint | ID | Story Title | Actor | Priority | Depends On | Pts |
| --- | --- | --- | --- | --- | --- | --- |
| S1 | US-042 | User Authentication (Login & Logout) | All Users | High | — | 5 |
|  | US-043 | Role-Based Access Control (RBAC) | System | High | US-042 | 8 |
|  | US-044 | Audit Trail — Log All System Actions | System | High | US-042 | 5 |
|  | US-045 | Security Rules (Session Timeout / Password) | System | High | US-042 | 5 |
|  | US-001 | Create & Manage Departments | Admin | High | US-043 | 3 |
|  | US-006 | Define Roles & Permissions | Admin | High | US-043 | 8 |
|  | US-007 | Configure System Settings | Admin | Medium | US-043 | 3 |
| S2 | US-002 | Add & Manage Doctors | Admin | High | US-001 | 5 |
|  | US-003 | Set Doctor Work Schedules | Admin | High | US-002, US-007 | 5 |
|  | US-004 | Create & Manage Rooms (Fixed Room Logic) | Admin | High | US-001 | 2 |
|  | US-005 | Add Staff Members (Receptionist & Nurse) | Admin | High | US-006 | 3 |
|  | US-033 | Manage Services & Pricing | Admin | Medium | US-007 | 2 |
| S3 | US-008 | Search for Existing Patient | Receptionist | High | US-009 | 3 |
|  | US-009 | Register New Patient | Receptionist | High | — | 3 |
|  | US-010 | View & Update Patient Profile | Recept./Doctor | Medium | US-009 | 3 |
|  | US-011 | View Available Appointment Slots | Receptionist | High | US-002,003,007 | 5 |
|  | US-012 | Book an Appointment | Receptionist | High | US-009,011 | 8 |
|  | US-013 | Validate Slot Availability (System) | System | High | US-012 | 5 |
|  | US-014 | Auto-Assign Room (Fixed→Dept→Manual) | System | High | US-004,012 | 5 |
|  | US-015 | Cancel or Reschedule Appointment | Receptionist | High | US-012 | 5 |
| S4 | US-016 | Check-In Patient on Arrival | Receptionist | High | US-012 | 3 |
|  | US-017 | Add Patient to Queue (System) | System | High | US-016 | 3 |
|  | US-018 | Prioritize Patient in Queue | Recept./Doctor | Medium | US-017 | 3 |
|  | US-019 | Skip or Recall Patient in Queue | Doctor | Medium | US-017 | 3 |
|  | US-020 | Call Next Patient | Doctor | High | US-017 | 3 |
|  | US-021 | Open Appointment & View Medical History | Doctor | High | US-020 | 5 |
|  | US-022 | Write & Save Diagnosis | Doctor | High | US-021 | 3 |
|  | US-023 | Write Prescription | Doctor | High | US-021 | 3 |
|  | US-024 | Add Consultation Notes | Doctor | Medium | US-021 | 2 |
|  | US-025 | Define Follow-Up Appointment | Doctor | Medium | US-021 | 3 |
|  | US-026 | Auto-Save Medical Record on Completion | System | High | US-022 | 5 |
| S5 | US-027 | Upload Medical Attachments | Doctor | Medium | US-026 | 5 |
|  | US-028 | View Complete Medical History | Doctor/Staff | High | US-026 | 3 |
|  | US-029 | Create Invoice | Receptionist | High | US-026,033 | 5 |
|  | US-030 | Calculate Invoice Total (System) | System | High | US-029 | 2 |
|  | US-031 | Process Payment | Receptionist | High | US-029 | 3 |
|  | US-032 | Generate Receipt (System) | System | High | US-031 | 3 |
|  | US-034 | Send Booking Confirmation Notification | System | High | US-012 | 3 |
|  | US-035 | Send Appointment Reminder Notification | System | Medium | US-034 | 3 |
|  | US-036 | Send Cancellation Notification | System | High | US-015 | 2 |
|  | US-037 | Send Payment Confirmation Notification | System | Medium | US-031,032 | 2 |
| S6 | US-038 | View Patient Count Reports | Admin | High | All ops | 5 |
|  | US-039 | View Revenue Reports | Admin | High | Epic-07 | 5 |
|  | US-040 | View Doctor Performance Reports | Admin | Medium | Epic-05,07 | 5 |
|  | US-041 | View Room Utilization Reports | Admin | Low | US-004 | 3 |
| GRAND TOTAL |  | 45 Stories |  |  |  | 176 |

PART 5 — STORY DEPENDENCY MAP

ترتيب التنفيذ الإلزامي — كل story لازم يكون dependencies بتاعتها خلصت قبل ما تبدأ:

| ID | Story | Depends On | Must Complete Before |
| --- | --- | --- | --- |
| US-042 | Auth | — | كل حاجة تانية في النظام |
| US-043 | RBAC | US-042 | كل الـ endpoints والـ business features |
| US-044 | Audit | US-042 | يشتغل cross-cutting من Sprint 1 |
| US-001 | Departments | US-043 | US-002, US-003, US-011 |
| US-002 | Doctors | US-001 | US-003, US-011, US-012, US-021 |
| US-003 | Schedules | US-002, US-007 | US-011, US-012 |
| US-004 | Rooms | US-001 | US-014 |
| US-005 | Staff | US-006 | Receptionist + Nurse login |
| US-009 | Register | — | US-012, US-016 |
| US-011 | View Slots | US-002, US-003, US-007 | US-012 |
| US-012 | Book Appt | US-009, US-011 | US-013, US-014, US-016, US-034 |
| US-014 | Auto Room | US-004, US-012 | يعمل تلقائياً على كل booking |
| US-016 | Check-In | US-012 | US-017 |
| US-017 | Queue | US-016 | US-018, US-019, US-020 |
| US-020 | Call Next | US-017 | US-021–US-025 |
| US-026 | Save Record | US-022 | US-027, US-028, US-029 |
| US-029 | Invoice | US-026, US-033 | US-030, US-031 |
| US-031 | Payment | US-029 | US-032, US-037 |
| US-038-041 | Reports | All ops epics | Sprint 6 فقط — بعد اكتمال البيانات |

Clinic Management System — Sprint Planning v2.0 ¦ April 2026 ¦ Confidential

6 Sprints  |  12 Weeks  |  45 User Stories  |  176 Story Points  |  4 Developers  |  2-Week Cadence